## Sheet1
Here’s the final version with all duplicates removed: | Week End date | Team Name | Team Member Name | Task Details | Status | Achievements | Blockers
| 2025-03-13 | Team 2 | Faria Afrin | 1. Attended internal and external standup. 2. JIRA Ticket: 580(expected behaviour was missing, Perform server side execution and get the data) 3. Review Bug ticket structure report 4. Jira Ticket: AEPT 362 5. Jira Ticket: AEPT 441 6. Jira Ticket: AEPT 597 7. Jira Ticket: AEPT 580 8. Jira Ticket: AEPT 592 1. Attended 3 meetings. 2. JIRA Tickets: AEPT 561 3. JIRA Tickets: AEPT 585 5. Prepare a checked box list to perform a test on story ticket AEPT 561. 6. Prepare a checked box list to perform a test on story ticket AEPT 580. 4. Perform exploratory testing. 1. JIRA Ticket: AEPT-289 2. JIRA Ticket: AEPT-563 3.JIRA Ticket: AEPT-609 4.JIRA Ticket: AEPT-608 5. Prepared test scenario checklist covering 18 scenarios for AEPT-589 1. Attended internal and external standups. 2. JIRA Ticket: 605 3.JIRA Ticket: 616 4.JIRA Ticket: 560 5.JIRA Ticket: 589 6. Write 18 cases for JIRA Ticket: 589 7. Write 8 cases for JIRA Ticket: 605 8. Write 10 cases for JIRA Ticket: 616 1. JIRA Tickets: AEPT-601 2. JIRA Tickets: AEPT-603 3. JIRA Tickets: AEPT-613 4. JIRA Tickets: AEPT-604 5. JIRA Tickets: AEPT-633 6. JIRA Tickets: AEPT-574 7. JIRA Tickets: AEPT-507 8. Perform 75+ cases combination for JIRA Tickets: AEPT-507 | Completed | 1.find out one issue, that is overlooked by their current QA 3. completed 158 tickets out of 160 1. Help developer to reproduce a bug which scenario was inconsistent, TPM appreciate it. 2. I improved the testing process by using a checklist for story tickets, saving time while ensuring proper validation. 3. Prepare slide on Monthly sync update for client. My immediate boss appreciate it. | 1. Unable to understand how their QA manage JIRA board
Internal and External Meetings | 2025-03-13 | Team 2 | Sadia Sultana Bristy | 23 Jira ticket 12 Jira ticket 14 Jira ticket 10 Jira ticket 1. Tested 8 Jira ticket 2. Attended Daily QA Standup. 3. Attended SP refinement meeting with Intact 4. Attended standup meeting with client of AUXO 5. Had several meetings with DEV 6. Reviewed the Figma design 7. Checked @vantage functionalities 1. Tested 6 Jira ticket 7. Went through transaction functionalities of S360 8. Checked some of the @vantage functionalities 1. Tested 18 Jira ticket | Completed | 1. Successfully tested 77 tickets, ensuring a smoother FI workflow and reducing potential blockers. 2. Discovered additional bugs during testing and promptly informed the team for resolution. 3. Worked closely with developers to troubleshoot and resolve issues, improving system stability. 4. Received positive feedback from the client for our quick and efficient ticket resolution. 5. Shared insights and suggestions with the team on optimizing functionality for a better user experience. 6. Maintained clear communication and strong collaboration to keep everything on track. 7. Reviewed and analyzed Figma designs to ensure alignment with project goals and user expectations. | Have not received KT session with Kyle
| 2025-03-13 | Team 2 | Nawsheen Ahmed Chowdhury | 1. completed 5/5 tickets. 1. Attended standup meeting with client of ANICO-DTC 2. Attended Daily QA Standup. 3. Attended meetings for all the QA members of AGT. 4. Regression testing of the application. 3. JIRA TICKET: AN-227 (Make LexisNexis account number a global variable) 4. BUG TICKET: AN-173 (Calculator - Switching from Premium Amount To Desired Payout Amount loses forecast) 5. BUG TICKET: AN-225 (Going back in app from the Cal Tool show different values) 3. JIRA TICKET: AN-114 (GA4 Script Implementation) 4. JIRA TICKET: AN-227 (Make LexisNexis account number a global variable) 3. Several 1:1 meetings with the automation engineer regarding test cases. 4. BUG TICKET: AN-126 (UI : Chart is cropped resulting into hiding years in x-axis) 5. BUG TICKET: AN-205 (The graph loading is inconsistant) 6. BUG TICKET: AN-225 (Going back in app from the Cal Tool show different values) 7. BUG TICKET: AN-228 (Banded Rates - Add condition to round up for 100k and 250k values) 8. BUG TICKET: AN-234 (Prod Issue: Format Agent Phone number that is returned from Verify User API) 9. BUG TICKET: AN-232 (Prod Bug: Redirect user who lands on login module to app login) 10. BUG TICKET: AN-233 (Prod Bug: Make Firelight script dynamic for Test vs. Prod environments) 3. BUG TICKET: AN-229 (Prod Bug: Transition screen does not appear on mobile after login) 4. BUG TICKET: AN-230 (Prod Bug: When a user comes from the calc email with a qualified link the values aren't populating later in the form) 5. BUG TICKET: AN-228 (Banded Rates - Add condition to round up for 100k and 250k values) 6. BUG TICKET: AN-231 (Prod Bug: Issue with send me my results email when desired payout amount is selected) 3. JIRA TICKET: AN-226 (Update the value guranteed spelling error) 4. Overview of the previously written test cases. 5. Monkey testing on the whole application. 6. Retesting 399 test cases. | Completed | Regression testing on the whole application. Covered all the test cases and retested them. ANICO DTC Product launch on 11th March 2025. Received appreciation on post-launch.
Meetings with Internal Members (Management + QA) | 2025-03-13 | Team 2 | Shaina Ferdous | 1. Attend Daily Standup with Ascensus team 2. Attend 1 to 1 meeting with Liam (TPM) 3. List down all the issues found in the Data Dictionary file and Figma wireframes given by client and update it in the Box file 1. Go over project docs and materials for Group 2 products in Confluence2. 2. Watch onboarding and discovery session meeting recording for Group 2 products Update Test Cases for the Admin panel of the project Test 2 Story tickets (APS - 4, APS - 6) 3. Daily Ascensus checkin meeting 4. Review updated data dictionary provided by client and update test cases accordingly 3. Mid-day check in meeting with dev team 4. Reviewed 24 issues shared by client 5. Write 10 test cases for Jira Ticket APS - 4 4. Write 16 new test cases for Jira Ticket APS - 23 5. Test 81 test cases for Jira Ticket APS - 21 4. Test 81 test cases for Jira Ticket APS - 21 | Completed | Key Achievements: 1. Conducted an in-depth review of Figma designs to ensure UI/UX consistency and functional accuracy, contributing to a seamless user experience. 2. Collaborated closely with developers to analyze system behavior, proactively identifying and resolving potential issues before they escalated. 3. Led comprehensive regression testing efforts, effectively preventing recurring defects and ensuring smooth, reliable updates. 4. Authored 67 detailed test cases, enhancing test coverage and improving product quality. Explored automation testing with Playwright, laying the groundwork for improved testing efficiency and scalability. Next Steps: 1. Expand and refine test cases to strengthen coverage for the upcoming development cycle. 2. Deepen expertise in Playwright automation, streamlining testing processes for greater efficiency. 3. Foster even stronger collaboration with the development team to accelerate issue resolution and optimize product quality. | My TPM is not assigning any new tickets for testing in my Jira Board. The team just instead gives me links to test the various different products and I log all the bugs i find in a separate google doc file as per the instructions of my TPM. As for my test cases, I am also maintaining them in a google sheet file which are linked to the Jira tickets created.
| 2025-03-13 | Team 2 | Md Muhaiminul Islam | 1. Attended daily Standup with AGT team 2. Attended Allianz - PHI project standup and discussed about the tasks we have done 3. Forked the Bitbucket repository and created local repo from where I have to push my code to original repo 4. Automated 7 negative test cases for primary care page of PHI application 2. Attended Allianz-PHI project standup and discussed about the work done 3. Automated rest of the test cases of primary care that were already in AIO 4. Pushed current commit to fork and created pull request after fixing the cases 3. Automated 9 New test cases of PHI application 3. Automated 11 new Test cases for Medical care page of PHI application 4. Made some adjustments to my existing script 2. Meeting with my TPM and other team members 3. Written 20 Test cases to AIO that were automated last day 4. Automated 14 new Test cases for Medical care page of PHI application 3. Automated 23 Test cases of medical history page of PHI application | Completed | Automated 7 negative test cases Successfully automated 9 new Test cases Successfully automated 11 cases Successfully automated 14 test cases and written 20 cases in the AIO Automated 23 test cases in a streak.
Resolving queries of Team Members | 2025-03-13 | Team 2 | Effat Jahan | "1. Daily QA standup 2. Sprint Demo Meeting with client 3. Daily Standup Penn Mutual 4. Sprint Retro Penn Mutual 5. Working on Test cases 6. Learning progress in Automation" 3. Penn Mutual Daily standup" 2. Attended Penn Mutual Daily standup 3. Took 3 interviews 4. Worked on 4 ticket writing steps to QA 5. Preparing their test cases for 4 tickets" 3. Backlog refinement Meeting 4. Writing Mock up test cases" 3. Writing Mock up test cases" 3. Writing mock tests" 3. Backlog refinement meeting 4. Writing mock tests" 3. Backlog refinement meeting 4. Two tickets assigned 5. Writing mock test cases " | Completed | "1. Conducted an in-depth review of Figma designs to ensure UI/UX consistency. 2. Written mock test for 18 tickets. 3. Made significant improvement learning automation testing"
| 2025-03-13 | Team 2 | Mufrad Mustahsin | "PQ- 2189 : Created reusable functions for all the logic components to be covered tested for one component , it worked ." Worked with PR changes of PQ-2189 , PQ-2190 --- all changes are pushed to PRs "Followed up on the new project update from Kyle; awaiting further details. Refining advanced Playwright concepts for enhanced automation efficiency. Strengthening TypeScript skills with a focus on automation." "Received an update about the new project from Kyle; he will share more details soon. Refining advanced Playwright concepts to enhance automation efficiency. Strengthening TypeScript skills with a focus on automation." "Waiting for new project to be assigned - In the meantime : Going through advanced OOP concept of JS" "Waiting for new project to be assigned - In the meantime : Going through advanced OOP concept of JS" | Completed | n/a | No project assigned yet
Help manual and automation SQAs | 2025-03-13 | Team 2 | Mufrad Mustavi | "1.Work on Jira Ticket - AEC -158 2. Raise Bug Ticket - AEC-273 3. Write 20 Test Cases for - AEC-262 4. Do regression testing for the whole system as per TPM instruction" "1. Write 22 Test Cases for - AEC-263 2. Do regression testing for the whole system as per TPM instruction" "1. QA Scrum Meeting 2. AEL Caps Daily Standup Meeting 3. Jira Ticket - AEC-158 4. Take 1 Interview 5. Work on Bug Tickets - AEC-273 6. Meetings with Dev 7. Write 10 Test Cases for" "1. Jira Ticket - AEC -158 2. Created Bug Ticket - AEC-283 3. Created Bug Ticket - AEC-286 4. Created Bug Ticket - AEC- 287 5. Attended Daily Standup with Client 6. Attended Planning/Grooming Session 7. Attend Dev team meeting 8. Attend AGT Scrum meeting 9. Take 2 Interview" 3. Meeting with Alexis and Harun 4. Meeting with Madhu 5. Raise Bug Ticket - AEC-302 6. Write 25 Test Cases - AEC-266" | Completed | Key Achievements:1. Conducted an in-depth review of Figma designs to ensure UI/UX consistency and functional accuracy, contributing to a seamless user experience.2. Collaborated closely with developers to analyze system behavior, proactively identifying and resolving potential issues before they escalated.3. Led comprehensive regression testing efforts, effectively preventing recurring defects and ensuring smooth, reliable updates.4. Authored 67 detailed test cases, enhancing test coverage and improving product quality.Explored automation testing with Playwright, laying the groundwork for improved testing efficiency and scalability.Next Steps:1. Expand and refine test cases to strengthen coverage for the upcoming development cycle.2. Deepen expertise in Playwright automation, streamlining testing processes for greater efficiency.3. Foster even stronger collaboration with the development team to accelerate issue resolution and optimize product quality. | This week, I was assigned only two new tickets. I spoke with the TPM, and they told me that next week they will assign me a bunch of tickets since the development side was working on this week.
| 2025-03-13 | Team 2 | Israth Jahan Nafi | "Story Ticket: RCPD 10,RCPD 9,RCPD 13 Test cases: 15" "1. Went through the Story which would be assigned to me soon for requirement Analysis(RCPD 5) 2. Raised 2 bug tickets under RCPD 10 3. Developed testcases regarding RCPD 10(Around 25)" "1. Jira Tickets: 2 Story tickets & 2 bug tickets 2. test Cases: 10 testcases for that " "1. Jira ticket: RCPD 10,11,12,14,09 2. testcases: 60 3. raised 3 major bugs while conducting confirmation testing" "Jira Ticket: RCPD 66 Bug Ticket: RCPD 74, 75 Test Cases: TC 1-12 for RCPD 66 Attended Daily Standup With AGT Attended Daily Stand Up with Auxo Analyzed the other User Stories(RCPD 5, RCPD 6) " "1. JIRA ticket: RCPD 66,5,6 2. New Bug Ticket Created: RCPD 80,81,74,75,79 3. Testcase Executed: 15 4. Regression Testing on Bug Ticket: RCPD 70, RCPD 71. 5" "1. Jira Ticket: RCPD 5 2. Bug Ticket: 80 3. Review Ticket: RCPD 50 4. Test cases: 10 5. Attended Daily Standup with Client 6/ Attended Daily Standup with AGT team 2B" | Completed | "Verified story tickets (RCPD5,6, 13) & raised intricate bug that could impact the client directly Added an observation that my TPM appreciated (A successfull message is needed once a user creates a new manager on Manager Research UI, as there was not any) Executed around 50 test cases for this week" | "1. Issue regarding the steps to QA(SA solved that later by adding other info) 2.Peer Group Median calculation was not added to the Steps to QA section 3.For the annual performance, after 2022 there was no annual performance for 2023 & 2024 4.Time Stamp was absent on the UI(Present at the User Story RCPD 10)" "1. The staging environment got updated so can not execute the testcases on the system 2.So need to talk to TPM"
Create setup functions and automated test cases | 2025-03-13 | Team 2 | Jabin Nessa | 2. Also had a meeting with Shishir vai about the VM and VPM issues. 3. Then had done the VM & VPN setup according to Shishir vai's instruction. 4. Had meetings Developer about tickets. 5. Tested 1 bug ticket. 6. Had some internal meetings " "1. Attended multiple meetings, our internal daily standup, Intact daily standup, ticket discussion meetings 2. Had a meeting with Intact QA 3. Done regression tests 4. Noted some anomalies in the system. " "1. Attended multiple meetings, internal daily standup, Intact daily standup, ticket discussion meetings 2. Had meetings with multiple team members 4. Noted some issues 5. Studied project overview videos." "1. Attended multiple meetings, internal daily standup, Intact daily standup, ticket discussion meetings 2. Had meetings with Dev 3. Tested 1 bug ticket. 4. Reported some bugs" "1. Attended multiple meetings, internal daily standup, Intact daily standup 2. Had meetings with different team members 3. Explored some functionalities. 4. Reported some bugs" "1. Attended multiple meetings, internal daily standup, Intact Sprint Planning meeting, ticket discussion meetings 2. Had meetings with internal team members 3. Explored some functionalities. 4. Reviewed 2 Story points." "1. Attended multiple meetings, internal daily standup, Intact daily standup 2. Had meetings with Devs about a ticket 3. Explored some functionalities. 4. Reviewed 1 Story point." | Completed | "1. Taken permission to test APIs which our previous QA didn't have. 2. Identified multiple bugs on the tested ticket also in the other modules through regression testing" Posted regression bug | The number of assigned tickets are very low
| 2025-03-13 | Team 2 | Mysha Parvin | "Went through the documentation Listed more points over Functional Document Attended Internal QA Meeting" 1. Completed Mojo Project's Process Flow 2. Attended the QA Team 2 SU 3. Went through Axis Case management flow " "1. Got access of the updated document 2. Found one more flowchart to check 3. Had a talk with TPM regarding the project's current status 4. Attended the Team 2A QA SU" 1. Looked into Functional Requirement document(10/18) 2. COMPLETED the Functional requirement document 3. Gave update to TPM 4. Listing more queries to discuss with TPM " | Completed | "1.Completed 4 documents' of the project to understand the flow and conditions 2.Raised 25 Queries in total till now over the project documentation 3.Attended Daily Meetings on time" | Project is at Discovery phase for 2 weeks now
Refactor test cases | 2025-03-13 | Team 2 | Sarataj Sultan | "1. Wrote 15 Test Cases 2. Solved 1 Jira Ticket (NYCCFBPA-281) 3. Daily AGT QA Standup 4. Meeting with TPM" "1. Solved 1 Jira Ticket (NYCCFBPA-282) 2. Daily AGT QA Standup 3. Meeting with TPM 4. Made around 10 comments to solve 2 bugs" "1. Reviewed the Master QA document of 3 Tickets and made several comments (found 2 bugs but didn't create tickets, cause today we had a client demo, and the application engineer resolved it). 2. Wrote around 25 test cases. 3. Attended Daily QA standup. 4. I found some blockers. TPM told me they will fix it tomorrow after a successful client demo." " 1. Work on Jira Ticket NYCCFBPA-283, NYCCFBPA-283 (still I have some blockers) 2. Write around 20 Test Cases 3. Did regression testing on a Module name Campaigns" "1. Bug Ticket Created (NYCCFBPA-346) 2. Worked on Story ticket (NYCCFBPA-282, NYCCFBPA-283) 3. Regression testing on the system." "1. Worked on Bug Ticket (NYCCFBPA-346) 2. Worked on Story ticket (NYCCFBPA-282) 3. Regression testing on the system. 4. Create Test Setup Function (Navigate_To_My_Leads_Setup) 5. Meeting with my TPM 6. Analyzed Story Ticket and Planned Test Cases" "1. Wrote 3 Setup Functions. 2. Wrote 20 Test Cases. 3. Worked on Jira Ticket (NYCCFBPA-282) 4. Worked on one Story point (Story Point 8 - Service Cloud)" "1. Wrote 2 Setup Functions. 2. Wrote 10 Test Cases. 3. Worked on Jira Ticket (NYCCFBPA-283) and Found 1 Critical Bug." | Completed | " Today or Tomorrow, we have a client demo. Instead of creating bug tickets, I communicated to the application engineer through the TAC Document to make that issue resolved by identifying issues and commented them." We had our first client demo. And I found some interesting bugs at the last moment. | I have some authorization related issues. TPM told me today she will solve that. I had some communication gap
| 2025-03-13 | Team 2 | Syed Elahi | "Internal and External Meetings Meetings with Internal Members (Management + QA) Resolving queries of Team Members and helping out where necessary Create setup functions and automated test cases Refactor test case Review Manual Test Cases Create Utility scripts Prepare documents, manual and report for Client" Prepare Bot for Client Prepare for Demo" Create Utility scripts Setup Bot for Client Review Code for Team Members" Help manual and automation SQAs Create setup functions and automated test cases Prepare report for Client Present report to Client Review Code for Team Members" Help manual and automation SQAs Create setup functions and automated test cases Work on Pipeline" | Completed | Internal and External Meetings – Participated in and facilitated discussions. Meetings with Internal Members (Management + QA) – Engaged in strategic and team-level discussions. Resolving Queries of Team Members – Assisted colleagues in overcoming challenges. Helping Out Where Necessary – Provided guidance and support to the team. Helped Manual and Automation SQAs – Supported both manual and automation testers. Created Setup Functions and Automated Test Cases – Developed test automation setups and test cases. Refactored Test Cases – Improved and optimized existing test cases. Reviewed Manual Test Cases – Ensured quality and coverage of manual test cases. Created Utility Scripts – Developed reusable scripts to improve efficiency. Prepared Documents, Manuals, and Reports for Clients – Compiled necessary documentation. Prepared Reports for Clients – Created structured reports for client communication. Presented Reports to Clients – Delivered reports in client meetings. Prepared for Demo – Organized and rehearsed for product demonstrations. Prepared a Bot for Client – Developed and configured a bot for client use. Set Up a Bot for Client – Deployed and integrated the bot into the system. Reviewed Code for Team Members – Provided code reviews to maintain high standards. Worked on Pipeline – Contributed to CI/CD automation and pipeline improvements. | Test cases written incorrectly by Auxo Manual QA
Review Manual Test Cases
| 2025-03-20 | Team 2 | Syed Elahi | Participated in internal and external meetings, including discussions with management and QA. Resolved queries of team members and provided necessary guidance. Assisted both manual and automation SQAs. Created setup functions and automated test cases. Refactored and reviewed manual test cases for quality assurance. Developed utility scripts to enhance efficiency. Worked on CI/CD pipeline automation. Automated test cases for improved testing coverage. Successfully completed two automation modules. Implemented unique and advanced automation solutions. Mentored and guided team members based on client feedback. Prepared structured reports for clients. | Completed | Successfully completed two automation modules. Refactored and automated multiple test cases, improving efficiency. Enhanced test coverage and quality by implementing advanced automation solutions. Provided guidance to team members, improving their performance. Assisted in pipeline improvements, streamlining CI/CD processes. Effectively prepared client reports and documentation. | Incorrect and missing test cases identified in manual QA, requiring additional review.
Create Utility Scripts | 2025-03-20 | Team 2 | Shaina Ferdous | Attended daily QA and Ascensus standup meetings. Participated in mid-day check-ins with the development team and meetings with application engineers. Performed extensive testing on various Jira tickets (APS - 21, APS - 23, APS - 11, etc.). Created and updated detailed test cases for multiple Jira tickets. Logged numerous bug tickets related to issues discovered during testing (e.g., APS - 284, APS - 285, APS - 289). Actively engaged in discussions about bug resolution and test case updates with TPM and project coordinators. Conducted functional and UI testing for multiple applications, with significant progress on testing 8 different products. | Completed | Completed and updated over 700 test cases, contributing to high-quality testing documentation. Successfully tested and logged detailed reports for multiple products, with reports completed for 2 out of 8 group 1 products. Provided bug reports for the identified issues in various Jira tickets. | Overwhelmed with workload: Assigned to test 8 different applications, retest bugs, and log new bugs, making it challenging to manage. The lack of additional manual QA resources is a key concern, as the workload is increasing with each product's deadline approaching (High). Difficulty in keeping up with the testing and documentation for all the tasks, leading to some feeling of overwhelm.
| 2025-03-20 | Team 2 | Sadia Sultana Bristy | Tested multiple Jira tickets, ensuring smooth workflow and minimizing blockers. Attended daily QA standups and standup meetings with the AUXO client. Conducted several meetings with developers to discuss system issues and improvements. Reviewed Figma designs to align them with project requirements. Analyzed transaction functionalities of S360 and @vantage. Participated in Jira board meetings with the client. Engaged in AUXO cross-meetings to enhance collaboration. Identified and reported additional bugs, ensuring timely resolution. Provided valuable suggestions to improve functionality and user experience. Ensured clear communication and teamwork to keep tasks on schedule. | Completed | Successfully tested 81 tickets, ensuring smooth FI workflow. Identified and reported additional bugs, contributing to system stability. Received positive feedback from the client for quick ticket resolution. Effectively collaborated with developers to resolve critical issues. Provided key insights on improving functionality and user experience. | No KT (Knowledge Transfer) session received from Kyle.
Automate test cases | 2025-03-20 | Team 2 | Sarataj Sultan | Wrote multiple test cases, including setup functions. Worked on Jira tickets, including defect validation and story ticket testing. Conducted regression testing on the Service Cloud module. Reviewed and analyzed the TAC document. Performed defect validation for reported issues. Successfully completed a sprint. Solved a story ticket as part of the testing process. | Completed | Successfully completed a sprint. Received appreciation from the Application Engineer. Wrote and executed multiple test cases, improving test coverage. Contributed to defect validation and regression testing. | Faced permission-related blockers impacting work progress.
| 2025-03-20 | Team 2 | Nawsheen Ahmed Chowdhury | Attended daily standup meetings with the ANICO-DTC client and daily QA standups. Worked on multiple Jira tickets, including updates and bug fixes (e.g., AN-226, AN-237, AN-236, AN-245). Performed monkey testing across the application. Retested and reviewed a large number of test cases (e.g., 399 and 339 test cases). Edited and prioritized test cases based on requirements. Collaborated with the automation engineer regarding the test cases. Performed regression testing to ensure system stability. | Completed | Successfully completed testing on 339 test cases during hypercare. Received appreciation post-launch for excellent performance. Received positive feedback from the client on fast ticket completion during hypercare. Played a key role in resolving issues and validating defect tickets, ensuring smooth functionality. | No significant blockers were reported.
Create utility functions | 2025-03-20 | team 2 | Israth Jahan Nafi | Attended multiple daily standup meetings with both AGT and Auxo teams, as well as one-on-one syncs with the UI engineer and TPM. Worked on multiple Jira tickets, including RCPD 5, RCPD 6, RCPD 50, and several bug tickets (RCPD 89, 90, 91, 92), addressing discrepancies and issues. Performed exploratory testing, closed bugs, and tested story tickets, such as RCPD 66, RCPD 5, and RCPD 11. Applied advanced techniques, like using Pandas for data analysis, to resolve data-related issues among 20,000 datasets for RCPD 50. Created and executed multiple test cases, including generating 14 test cases for RCPD 11. Raised business discrepancies (e.g., RCPD 79), identified missing steps, and provided insights to save the team from making mistakes in the UAT phase. Reviewed and closed multiple tickets successfully, including RCPD 10, 86, and bug tickets like RCPD 59, 61. | Completed | Closed major tickets and bugs successfully with high priority and provided detailed feedback to the team and TPM. Played a critical role in identifying and addressing discrepancies that impacted the system's behavior, ensuring smoother project progress. Contributed significantly to the progress of the project by completing assigned tickets and providing helpful feedback for ticket requirements. Attended all required meetings and syncs, providing valuable support to the team and UI engineer. | RCPD 50: Encountered discrepancies with the test steps and data matching, which delayed progress. RCPD 66: Identified a contradiction between the dashboard and search functionality, raising a business discrepancy. Several bug tickets from the RCPD 6, 66, 77, 13, and 7 have incomplete information from the development side, affecting the overall ticket resolution.
| 2025-03-20 | Team 2 | Faria Afrin | Jira Ticket Handling: Worked on a variety of Jira tickets, including AEPT-613, AEPT-507, AEPT-566, AEPT-427, AEPT-581, AEPT-612, AEPT-291, AEPT-596, AEPT-564, AEPT-585, AEPT-638, AEPT-645, AEPT-646, and AEPT-652, addressing various testing requirements across different functionality. Bug Resolution Assistance: Successfully assisted developers in reproducing a bug due to inconsistent scenarios, leading to a resolution after troubleshooting. Edge Case Testing: Covered 9 edge cases for AEPT-566, ensuring the application was tested for rare and unusual conditions. Collaboration and Communication: Actively participated in QA sync meetings, internal and external standups, and collaborated with developers to clarify testing steps and resolve issues. Monthly Sync Report: Prepared a Monthly Sync Report for Kyle, which was positively received by both the client and AGT for its detailed approach and thoroughness. Ticket Progress: Successfully tested and reported on various Jira tickets, providing proper test coverage and addressing blockers along the way. | Completed | Positive Client Feedback: The client praised Faria's testing approaches during the monthly sync, recognizing the thoroughness and detail in the testing. Developer Appreciation: Developers appreciated Faria's test checklist, which was used as a reference during ticket closure to ensure quality and consistency. TPM Praise: The TPM acknowledged Faria’s testing approaches during the one-on-one meeting, further highlighting the effectiveness of their work. | Testing Blocker: Unable to proceed with testing due to a blocker related to AEPT-656. This hindered further progress until the issue is resolved.
Generate report | 2025-03-20 | Team 2 | Mufrad Mustavi | Attended Daily Standup meetings with the client and AGT. Participated in QA Scrum and QA Sync meetings. Worked on Jira Tickets (AEC-158, AEC-8). Raised bug tickets (AEC-302, AEC-304, AEC-305). Wrote 25 detailed test cases (AEC-266). Performed regression testing across the system. Attended interviews and planning/grooming sessions. Collaborated with developers to investigate and resolve bugs. Researched and implemented Playwright for automation testing. | Completed | Completed 60 test cases, enhancing test coverage. Successfully identified and resolved bugs in collaboration with developers. Implemented automation testing with Playwright, improving efficiency and scalability. | Unable to perform QA on the QA environment as some modules have not been promoted. Ticket functions worked well on the staging environment, but further testing is pending once modules are promoted (Medium).
| 2025-03-20 | Team 2 | Effat Jahan | Daily Standups: Attended the QA and Penn Mutual standup meetings. Participated in backlog refinement meetings and sprint planning. Worked on multiple Jira tickets (e.g., PML-101, PML-106, PML-175, PML-28, PML-203, PML-204). Contributed to Multilife Screen design review and conducted a KT session with a new QA. Wrote and updated test cases (e.g., 70 test cases). Attended sprint demos and retrospectives. | Completed | Completed all tickets assigned for the week and contributed to a smooth sprint demo. Successfully completed and moved tickets to done with a high rate of test case completion. Client appreciation for proactively requesting tickets to be finished two days before the project deadline, ensuring timely testing. | Time crunch before sprint demos: Was assigned tickets just two hours before the client demo, making thorough testing and bug refactoring challenging. The lack of QA-UAT promotion in the early stages of the project made it difficult to test in the appropriate environment. Suggestions: Advocated for receiving tickets earlier in the sprint to ensure proper testing and bug resolution.
Prepare documentation | 2025-03-20 | Team 2 | Mysha Parvin | Functional Requirement Documentation: Reviewed and completed 10 pages of the functional requirement document and successfully finished it by 3/14. Attended Daily QA Standup and Team 2 QA Standup meetings regularly. Worked on listing queries related to the documentation and awaiting responses from the TPM. Provided daily updates and submitted daily update forms. Shared meeting recordings and provided updated flowcharts for review. Took interviews and contributed to team efforts. | Completed | Successfully completed functional requirement documentation and attended meetings on time. Took initiative to list more queries for TPM discussion and followed up on pending updates. Shared valuable information, including flowcharts and meeting recordings to support the team. | Project's development has not started yet, with no major updates from TPM. Daily Standups for Axis Mojo project are not consistently happening. Awaiting responses to queries from TPM and the next steps for the project to move forward.
| 2025-03-20 | Team 2 | Jabin Nessa | Meetings: Attended multiple meetings including internal daily standups, Intact daily standups, and cross-team meetings like AUXO. Participated in discussions with developers and Intact QA to clarify issues and test tickets. Explored functionalities and tested bug tickets, creating and logging issues when necessary. Conducted regression testing and participated in QA sync meetings. | Completed | Successfully tested and logged bug tickets. Contributed to cross-team communication and collaborated with internal teams. Completed regression testing, helping improve the overall stability of the application. | Need permissions to access certain internal applications to complete testing. Lack of business knowledge in some modules affected testing, but discussions with relevant team members should resolve it soon.
Plan for test automation optimization and efficiency | 2025-03-20 | Team 2 | Md Muhaiminul Islam | Automated Testing: Muhaiminul has been automating test cases for the Medical History page of the PHI application, completing various critical and negative test cases. He also developed reusable methods to improve efficiency and maintainability. Collaborations & Meetings: Attended daily stand-ups with both the AGT QA team and the PHI project team, collaborated with the TPM and developers for project refinement discussions, and participated in code reviews and issue resolutions. Code Contributions: Pulled the latest code from Bitbucket, resolved merge conflicts, and made improvements to the test scripts. Regression & E2E Testing: Ran E2E regression scripts and medical history tests in the QA environment. | Completed | Test Automation: Successfully automated a total of 66 test cases across multiple days, completing the Happy Path for the Medical History page. Utility & Code Improvements: Developed utility methods and reviewed test cases for comprehensive coverage of functional and validation scenarios. Positive Feedback: Received recognition from the Engagement Director for showing curiosity and taking an active role in the RSP project's automation plan. | No significant blockers were reported. The automation work is proceeding smoothly with no major challenges affecting progress.
| 2025-03-20 | Team 2 | Mufrad Mustahsin | Onboarding to New Project: Mufrad was onboarded to the Ascensus project and quickly became involved in testing the JP Morgan flow. Test Cases: He tested 174 test cases in one day, indicating a high level of productivity and speed in his work. Bug Reporting: Raised 3 bug tickets related to UI issues encountered during testing. | Completed | Quick Onboarding: Mufrad managed to get onboarded to the project efficiently, tackling a large volume of test cases in a short time frame. Testing Excellence: Successfully tested a substantial number of test cases (174) and identified UI issues that needed attention. Bug Reporting: Proactively raised 3 bug tickets, contributing to the project's bug-fixing process. | UI Issues: Encountered UI issues that needed to be reported, which could potentially delay the progress of testing if not addressed.
Onboard new QA |  | Team 2 |  |  | Select
2025-03-21 | 2025-03-27 | Team 2 | Syed Elahi | Tested 11 Jira ticket Tested 10 Jira ticket Attended Daily QA Standup Attended standup meeting with client of AUXO Had several meetings with DEV Attended 2 standup meeting with Intact & Auxo Discussed the new tickets and requirements Meeting with a developer regarding task Had Jira Board meeting with client Tested tickets: SUP-13304, SUP-13410, SUP-13595, SUP-13650, SUP-13799, SUP-13809, SUP-13812, SUP-13813, SUP-138774 Tested overall FI workflow (Set up Account, submission, edit submission, Quote-FI, transaction details, @vantange Pricing and coverage functionality) | Completed | Optimized automation framework to speed up test automation, debugging and speed | N/A
2025-03-21 | 2025-03-27 | Team 2 | Shaina Ferdous | Attend Daily QA standup Attend Daily Ascensus standup / Daily Standup with Ascensus Attend End of Day status update call with Ascensus Attend 1 on 1 internal KT sessions with new QA added to the team Attend Ascensus QA Discussion with Kyle Attend Ascensus Start of Day meeting Attend meeting with the Ascensus QA team Attend Ascensus End of Day meeting Complete testing 176 test cases for Jira Ticket APS - 13 Test 2 Bug Tickets (APS - 294, APS - 296) Test 16 Bug Tickets (APS - 304, APS - 298, APS - 296, APS - 339, APS - 363, APS - 325, APS - 365, APS - 299, APS - 353, APS - 356, APS - 359, APS - 294, APS - 307, APS - 350, APS - 309, APS - 372) Create 5 Bug Tickets in Jira (APS - 382, APS - 393, APS - 396, APS - 397, APS - 398) Create 5 new bug tickets in Jira (APS - 399, APS - 400, APS - 402, APS - 403) Did regression testing on 2 Jira Tickets (APS -284, APS - 339) Test 11 Bug Tickets (APS - 362, APS - 395, APS - 356, APS - 344, APS - 332, APS - 326, APS - 325, APS - 294, APS - 324, APS - 346, APS - 288) Create 9 new bug tickets in Jira (APS - 432, APS - 433, APS - 434, APS - 435, APS - 436, APS - 437, APS - 438, APS - 441, APS - 443) Performed 208 test cases and updated test case document Create 6 Bug Tickets in Jira (APS - 498, APS - 502, APS - 504, APS - 508, APS - 517, APS - 538, APS - 546) Complete 556 test cases and updated test case document | Completed | Successfully completed QA report for 2 out of 8 Group 1 products for Ascensus. 1600+ test cases were completed by the Ascensus QA team for all 8 products in Group 1. Full UI and Functional testing was completed with the help of 4 QAs across all 8 products. These products are now ready to go into UAT soon. | Request for Additional Support: Clearly communicate the current challenges to your manager and team lead, mentioning the resource gap due to Mufrad's absence and Asif's limited availability. Stress the importance of getting additional help, whether through a temporary QA member or re-assigning someone from another project, to ensure the testing phase goes smoothly and deadlines are met. Prioritization: Consider collaborating with your team and product owners to prioritize testing on the critical functionalities. This way, you can ensure that the most important parts of the product get the most testing focus, and any non-essential features can be either skipped or tested later. Tracking Bugs: Since you're struggling to track bugs effectively, try utilizing tools like JIRA or a bug-tracking sheet that automatically updates to give you an overview of what's been tested, what's pending, and what bugs need immediate attention. If possible, delegate some of the bug tracking to other team members.
2025-03-21 | 2025-03-27 | Team 2 | Sadia Sultana Bristy | Tested Jira tickets (approximately 10–11 tickets) Attended Daily QA Standup Attended standup meeting with client of AUXO Had several meetings with DEV Attended 2 standup meetings with Intact & Auxo Discussed new tickets and requirements Met with a developer regarding tasks Had a Jira Board meeting with the client Tested SUP tickets: SUP-13410, SUP-13595, SUP-13650, SUP-13812, SUP-13799, SUP-13813, SUP-13809, SUP-138774, SUP-13304 Tested overall FI workflow (Set up Account, submission, edit submission, Quote-FI, transaction details, @vantange Pricing and coverage functionality) | Completed | - Completed testing on 44 tickets, contributing to a smoother FI workflow and minimizing roadblocks. - Detected and reported bugs during testing, ensuring timely resolution by the team. - Collaborated closely with developers to troubleshoot and address issues effectively. - Received positive feedback from the client for our responsiveness and efficiency in resolving tickets. - Maintained clear communication and strong collaboration to keep everything on track. | N/A
2025-03-21 | 2025-03-27 | Team 2 | Sarataj Sultan | Reviewed and analyzed the TAC document (including making comments) Wrote test cases (ranging from a few to around 15) Developed test setup functions Solved a Story ticket Performed regression testing (on the system, Partner Module, and Campaign Module) Held discussion with TPM about the current sprint | Completed | N/A | Didn't get any story ticket due to development delay.
2025-03-21 | 2025-03-27 | Team 2 | Nawsheen Ahmed Chowdhury | Attended standup meeting with client of ANICO-DTC Attended Daily QA Standup Attended Monthly QA Sync-up meeting with Kyle Reviewed previously written 339 test cases Tested the whole application in UAT and Staging Performed exploratory testing on the application Verified and tested rate calculation (JIRA Ticket: AN-207) | Completed | N/A | N/A
2025-03-21 | 2025-03-27 | Team 2 | Israth Jahan Nafi | Attended Daily Standup with AGT & Auxo Attended meeting with Auxo Attended meeting with Esha Tested Story Tickets: RCPD 11, RCPD 12, RCPD 7, RCPD 77 Retested Story Tickets: RCPD 105, RCPD 116, RCPD 117, RCPD 108 Reviewed Story Tickets: RCPD 12, RCPD 16 Closed Story Tickets: RCPD 11, RCPD 6 Closed Bug Tickets: RCPD 59, RCPD 91, RCPD 92, RCPD 93, RCPD 82, RCPD 89, RCPD 61 Raised Bug Tickets: RCPD 101, RCPD 102, RCPD 104 Assigned New Bug Tickets: RCPD 97, RCPD 98, RCPD 99 Found bugs and created tickets: RCPD 12 → RCPD 101, 102, 104, 105 RCPD 16 → RCPD 106, 107, 108, 109 RCPD 20 → RCPD 110, 111, 112, 113 RCPD 7 → RCPD 114 Developed test cases: RCPD 11 → 14 test cases RCPD 66 → Around 10 test cases Performed RCPD 50 Testing (Checked HTML & Plain Text) | Completed | Raised around 90% of the showstopper bugs Found some business gap while testing(Between description VS UI) Wrote down around 100 test cases | There are some tickets in the Ready for QA/In QA that have blockers to complete: RCPD 66 (With Bug Ticket 79) RCPD 77 (Steps to QA description blocker) RCPD 13 (Blocker with 40) RCPD 7 (Blocker with Bug Ticket RCPD 79) For the rest of the tickets, I had blockers to complete those last day I informed my TPM. There are 3 tickets I won’t be able to complete due to blockers: RCPD 66 – Blocked by bug ticket RCPD 79, which is not yet ready for QA. RCPD 13 – As per the comments, I can proceed once RCPD 40 is ready, but it is not yet available for QA. RCPD 77 – The steps for QA are incomplete, so I’m unable to proceed.
2025-03-21 | 2025-03-27 | Team 2 | Faria Afrin | Worked on JIRA Tickets: AEPT-1, AEPT-44, AEPT-256, AEPT-256, AEPT-567, AEPT-600, AEPT-622, AEPT-623, AEPT-626, AEPT-629, AEPT-630, AEPT-631, AEPT-632, AEPT-638, AEPT-649, AEPT-651, AEPT-654, AEPT-655, AEPT-656, AEPT-657, AEPT-658, AEPT-660, AEPT-661, AEPT-662, AEPT-665, AEPT-677, AEPT-678, AEPT-679, AEPT-680 Closed JIRA Tickets: AEPT-623, AEPT-600, AEPT-626, AEPT-629 Raised JIRA Tickets: AEPT-681, AEPT-682, AEPT-684 Performed exploratory testing Created test scenarios: AEPT-256 → 10 test scenarios AEPT-567 → 13 test scenarios Other tasks → 9 test scenarios Executed test scenarios: 23 test scenarios in total Additional 16 test cases executed separately Attended meetings: 4 meetings in total Internal and external standups | Completed | TPM appreciated my test approaches in the one-on-one meeting. Before wrapping up for the holiday, I was trying to complete the NBP tickets from my end (with accuracy), and I did it. | N/A
2025-03-21 | 2025-03-27 | Team 2 | Mufrad Mustavi | JIRA Tickets Worked On: AEC-158, AEC-261, AEC-264, AEC-271, AEC-280, AEC-281, AEC-292 Bug Tickets: Raised: AEC-308, AEC-314 Worked On: AEC-271 Test Case Writing: AEC-264 → 55 test cases AEC-292 → 80 test cases Meetings Attended: AGT Standup Auxo Standup Development Team Meeting Meeting with Harun Additional Tasks: Conducted 1 interview | Completed | Key Achievements: 1. Collaborated closely with developers to investigate and diagnose bugs, ensuring timely identification and resolution to maintain system stability. 2. Authored 135 detailed test cases, enhancing test coverage and improving product quality. 3. Find a major bug in the QA environment - An extra blank form is being created in the Forms section of the View Filing page when creating a new filing. | Unable to check some fucntionality, because some of the module is not promoted to QA environment. Today maybe the dev team will promoted those module Did not receive any tickets as all tickets are in Peer Review. Afterr the review is done they will give me the tickets
2025-03-21 | 2025-03-27 | Team 2 | Effat Jahan | Meetings Attended: Daily QA Standup Penn Mutual Daily Standup Test Case Writing: General: 15+ test cases written Modules Worked On: Plan Census Module: PML-TC-5.1 to PML-TC-5.11 Plan Navigation Plan Details UI Pages | Completed | Before sprint 3 ending, I have collaboratively worked with the devs of Penn mutual project. Did last minute on the fly testing with the dev on call and raised 8 bug tickets for one single ticket doing functional testing on it. Got appreciation from the devs and the quick fixes helped finish the ticket in really fast. Showed client all the test cases that are written till date. | No tickets are assigned to me currently. No new tickets assigned to me yet, as the QA environment promotion is still pending. Currently working on writing test cases for the module. No tickets assigned to me yet as most tickets are facing some sort of blocker.
2025-03-21 | 2025-03-27 | Team 2 | Mysha Parvin | Meetings Attended: Daily QA Standup Monthly meeting with Kyle Meeting with TPM regarding updated requirements Meeting with Liam and Yashica Ascensus QA Sync Meeting & End-of-Day Meeting KT Session for Ascensus Work Updates: Project Onboarding: Joined Ascensus project Testing Activities: Tested Advisor Flow and Sponsor Flow (UI & Functional Testing) Assigned Ascensus IK - Daily Level Comp (50) for testing Executed around 170 test cases Updated test case statuses Bug Tracking: Bugs Raised: March 26: APS-465, APS-474, APS-475, APS-476, APS-478, APS-483, APS-487, APS-490 Later Entries: APS-499, APS-503, APS-506, APS-520, APS-522, APS-529, APS-534, APS-537, APS-544 Latest: APS-586, APS-582, APS-581, APS-580, APS-579, APS-570, APS-565, APS-564, APS-562, APS-561, APS-559 Bugs Tested & Closed: APS-442, APS-481 Administrative Tasks: Submitted Previous Day Update Form | Completed | Attended all the meetings throughout the week on time. Successfully onboarded to a new project. Attended a KT session for the first time. Successfully completed Functional, UI, and Content Testing. Received positive feedback from the client and team lead on the speed of ticket completion. Successfully tested 35 test cases and created 8 bug tickets. Successfully tested 170 test cases. Successfully raised 9 bug tickets after functional testing. Successfully closed 2 bug tickets and raised 11 new bug tickets. Got positive feedback from the client and team lead. Successfully completed the full flow of Pershing for Content testing. | No task assigned. No standup meeting is conducted for the project. 9 JIRA tickets are under Blocked/Need more info status.
2025-03-21 | 2025-03-27 | Team 2 | Jabin Nessa | Meetings Attended: Internal Daily Standup Intact Daily Standup AUXO Transaction Team Ticket Discussion Intact Work Update with Sakib Vai Meetings with Internal QA and Developers Testing Activities: Regression Testing Completed Bug Tickets Tested: 1-2 per session Test Cases Written: 2 Bug Tracking: Bugs Reported: 1 per session | Completed | Found some regression bugs | Need access to some internal application/software to test some tickets.
2025-03-21 | 2025-03-27 | Team 2 | Md Muhaiminul Islam | Meetings Attended: Daily Standup with AGT RSP Daily Standup Allianz PHI Project Standup Auxo Weekly Refinement Meeting for RSP Project AGT QA Standup Meeting Meeting with Project Team (PHI) Automation & Development: Resolved merge conflicts and created a Pull Request to Kyle Reviewed use cases: AZL-916 Started automation for special bug cases of the PHI project Implemented methods for PHI project test files Automated issues: No. 933, No. 967 Created separate methods to support use cases Testing & Execution: Ran E2E regression script and medical history script, shared reports Completed two negative use cases for AZL-916 ticket Reviewed 3 bug tickets and automation use cases Performed device QA manual testing on Chrome & Edge (PHI Interview - 7 pages, 7 user scenarios) | Completed | Attended Daily standup with AGT (1st day of week) Attended RSP daily standup Participated in Allianz PHI project standup Worked and completed two Negative use cases of AZL-916 ticket Adjusted previous E2E regression script Attended Allianz PHI standup with Auxo team Ran E2E regression script and shared the report Ran Medical History special cases script and shared the report in the group Reviewed 3 Bug tickets and their automation use cases Reshaped the previous test cases Started working on the Special bug cases of the PHI project to automate; implemented some methods for the test file Attended Auxo weekly refinement meeting for the RSP project Performed device QA manual testing for Chrome and Edge browsers on a Windows machine, covering the entire PHI interview path and submitting (7-page application; tested 7 user scenarios) Automated Issue no. 933 ticket Automated Issue no. 967 ticket Created separate methods to support the use cases | N/A
2025-03-21 | 2025-03-27 | Team 2 | Mufrad Mustahsin | Meetings Attended: Ascensus QA Standup Ascensus Start of Day Meeting Ascensus QA Sync AGT Standup 2 External Meetings 1 Internal Meeting KT Sessions Testing & Execution: Tested 174 test cases Tested all high-priority bug tickets (around 14) Tested UI & functional aspects for multiple products Bug Reporting & Discussions: Logged over 20 bug tickets Raised 3 bug tickets Discussion with the dev team regarding issues | Completed | Tested 174 test cases in one day & raised lots of UI issues after just being added to the project. Within short period of time tested and logged overall 225 plus tickets | Didn't get any story ticket due to development delay. My TPM told me to focus on writing test cases.
|  | Team 2 |  |  | Completed
2025-04-03 | 2025-04-11 | Team 2 | Israth Jahan Nafi | Completed extensive testing and review of over 500+ tasks including stories and bugs, achieving high test coverage and closing critical sprint tickets. | Completed | Delivered 100% assigned tasks, raised significant business-critical bugs, ensured end-to-end testing with ~95% coverage, supported developers with detailed reviews, and improved efficiency under tight timelines. | Faced blockers due to bugs, missing instructions, and unclear requirements—initially high in volume but gradually resolved toward week's end.
2025-04-03 | 2025-04-11 | Team 2 | Shaina Ferdous | Completed over 3,400 test cases across various environments and tickets, covering multiple products with consistency and thoroughness. | Completed | Performed exceptional volume of testing, worked overtime, led and coordinated the QA team, and received personal appreciation from the TPM for leadership and ownership. | Major blocker due to underperforming teammate and last-minute task allocations from project management, significantly affecting productivity.
2025-04-03 | 2025-04-11 | Team 2 | Sadia Sultana Bristy | Tested 60 Jira tickets, validated the complete FI workflow multiple times, and created a client-facing demo video. | Completed | Successfully pushed FI workflow to UAT. Identified a critical functionality bug. Earned appreciation from both TPM and AUXO team. Created a demo video showcasing the workflow to the client. | Facing high-impact technical issues with a slow and unstable VM, causing disconnections and black screens that hinder workflow.
2025-04-03 | 2025-04-11 | Team 2 | Mufrad Mustavi | Completed 90 tasks, including high-priority bug fixes, new feature testing, and extensive QA efforts across multiple Jira tickets. | Completed | Identified and raised a critical bug that impacted core functionality. Completed 10 high-story-point tickets. Received direct appreciation from TPM for consistent, high-impact contributions. Actively participated in AGT and Auxo meetings while maintaining strong delivery momentum. | None reported.
2025-04-03 | 2025-04-11 | Team 2 | Effat Jahan | Completed 60 tasks across multiple Jira tickets, with detailed test case creation and coordination with the dev team on large, high-story-point items. | Completed | Received High Five from the team and client for early and efficient completion before the demo. Delivered extensive testing on high-story-point tickets like PML-185, PML-243, and PML-166. Maintained steady collaboration with QA and Dev teams through daily standups and syncs. | None reported.
2025-04-03 | 2025-04-11 | Team 2 | Sarataj Sultan | Completed 44 tasks including regression testing, test case creation, and review of TAC documentation; assisted in functional prep by working on test setup functions. | Completed | Made detailed contributions to TAC documents with thoughtful comments. Carried out test planning and case writing proactively, even when testing was on hold. Successfully picked up and worked on story tickets: NYCCFBPA-292, 293, 296, 297, 300. | Story Ticket Delays: Development delay impacted testing availability early in the week. TPM Instruction: Testing paused on one day to focus on documentation/case writing. Permissions: Encountered access issues while handling some stories.
2025-04-03 | 2025-04-11 | Team 2 | Jabin Nessa | Participated in all key meetings, collaborated with team members, explored the application, wrote test cases, and supported teammates while completing all assigned tasks. | Completed | Successfully maintained consistent task completion across the week and helped peers understand functionality, demonstrating initiative and team collaboration despite access limitations. | High-impact blockers include lack of access to internal tools, limited availability of tasks, and insufficient project knowledge.
2025-04-03 | 2025-04-11 | Team 2 | Nawsheen Ahmed Chowdhury | Attended multiple standup meetings, performed regression and exploratory testing, retested 339 test cases across different environments (QA, UAT, Staging), logged multiple bug tickets, and worked on JIRA tasks. | Completed | Completed regression testing across all environments, performed extensive exploratory testing, and identified major bugs. Consistently managed large volumes of testing and ticket handling with high efficiency. | None reported.
2025-04-03 | 2025-04-11 | Team 2 | Faria Afrin | Worked on multiple JIRA tickets, attended daily standup meetings with clients and internal teams, executed around 165 test scenarios, and worked on bug reports and detailed test case planning. | Completed | Successfully completed comprehensive regression testing, created reusable test data sets, maintained clean test environments, and earned TPM appreciation for detailed bug reports. Efficiently logged and tracked issues. | None reported.
2025-04-03 | 2025-04-11 | Team 2 | Mysha Parvin | Worked on multiple JIRA tickets, completed full regression testing for multiple environments (QA & DEV), moved tickets to UAT, and performed happy path and functional testing. Also assisted team members with their tasks after completing own. | Completed | Successfully moved tickets to developers with proper clarification, added test cases to the Sales flow test sheet, completed UI and functional testing for Sales Flow, and completed all assigned tickets. Also, helped team members after finishing personal tasks. | Blocked tickets passed with more information and handled multiple rework tickets.
2025-04-03 | 2025-04-11 | Team 2 | Md Muhaiminul Islam | Completed and tested several test cases for RSP and PHI projects. Participated in standups, meetings with developers, and reviewed use cases and test documentation. Also, ran automated tests for PHI and researched API automation integration with Playwright. | Completed | Completed key test scenarios and tickets for RSP, including a complex test case that was vital for UAT promotion. Collaborated effectively with developers to ensure the test procedures were aligned with expectations. | None reported.
2025-04-03 | 2025-04-11 | Team 2 | Mufrad Mustahsin | UAT feedback tickets and overall product flows were tested consistently throughout the week. | Completed | Maintained consistent output with full task completion and no blockers—demonstrates strong reliability. | None reported.
2025-04-03 | 2025-04-11 | Team 2 | Syed Elahi | Led and executed automation tasks, resolved team queries, reviewed test cases and tickets, and supported meetings across teams. | Completed | Refactored and improved the automation framework, automated test cases across multiple modules, and played a key role in unblocking team issues. | Encountered high-impact blockers due to system regressions and UI/attribute changes affecting test automation.
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select